## Plan
Tibba website — plan to launch (weekdays only, 15–30 Oct)
Up to 3 tasks share a day. Yellow rows are buffer days: fixes, adjustments and rework only, no new work. Update the blue Status column as you go.
Task | Description | Status | Rough Deadline
Finish the About hero | Final design of the About page hero, checked on desktop and phone | Not started | 2026-10-15
Case study layout | One shared layout for all four case studies (sections, image sizes, results block) | Not started | 2026-10-15
Collect case study content | Text, images and results for all four case studies in one folder | Not started | 2026-10-15
Case study 1: Groww | Design and build the page, desktop and phone | Not started | 2026-10-16
Case study 2: Firstpost | Design and build the page, desktop and phone | Not started | 2026-10-19
Case study 3: Breathe ESG | Design and build the page, desktop and phone | Not started | 2026-10-20
Case study 4: Shyft | Design and build the page, desktop and phone | Not started | 2026-10-21
Send for client review | Share the About hero and all four case studies for feedback | Not started | 2026-10-21
BUFFER 1: review fixes | Fixes, adjustments and rework from the client review | Not started | 2026-10-22
Phone check, every page | Real iPhone and Android: layout, text size, scrolling, animations | Not started | 2026-10-23
Proofread all copy | Spelling, names and numbers checked against the client's figures | Not started | 2026-10-23
Domain and hosting | Point the domain at the hosting, HTTPS on, www and non-www sorted | Not started | 2026-10-23
Basic SEO | Page titles and descriptions, share image, alt text, sitemap, robots.txt | Not started | 2026-10-26
Analytics and tracking | Analytics live; contact form and "Book a call" clicks tracked | Not started | 2026-10-26
Speed | Compress images and videos, load heavy parts late, check PageSpeed on mobile | Not started | 2026-10-26
BUFFER 2: phone and speed fixes | Fixes, adjustments and rework from the phone check and speed work | Not started | 2026-10-27
Full test on browsers and devices | Chrome, Safari, Firefox, Edge; iPhone and Android; every link and button | Not started | 2026-10-28
Contact form test | Send real test messages; check they arrive in the right inbox | Not started | 2026-10-28
Backup before launch | Note the current version so it can be restored in one click | Not started | 2026-10-28
BUFFER 3: final fixes | Last fixes, adjustments and rework; final sign-off from the client | Not started | 2026-10-29
Launch | Switch the live domain to the new site | Not started | 2026-10-30
Submit sitemap to Google | Add the site to Google Search Console and submit the sitemap | Not started | 2026-10-30
Watch after launch | Check analytics, forms and pages through the day; fix anything urgent | Not started | 2026-10-30

## Launch checklist
Before going live — checklist |  |  |  | Done
Set "Done?" to Yes as you go (blue column). Use N/A for anything that does not apply.
Area | Item | Done? | Notes
1. Domain and hosting | Domain is registered and set to renew automatically (check the card on file) | No
1. Domain and hosting | Domain points to the hosting (e.g. Vercel): www and the bare domain both open the site | No
1. Domain and hosting | HTTPS padlock on every page; http:// sends visitors to https:// | No
1. Domain and hosting | One address wins: www goes to the bare domain (or the other way round), never both | No
1. Domain and hosting | Old site links (if any) redirect to the matching new pages | No
1. Domain and hosting | Email on the domain still works after the switch (check the MX records are unchanged) | No
2. Basic SEO | Every page has its own title (under 60 characters) and description (under 155) | No
2. Basic SEO | Share image set, so links look right on LinkedIn, WhatsApp and Slack | No
2. Basic SEO | Favicon shows in the browser tab | No
2. Basic SEO | Every image has short alt text | No
2. Basic SEO | One main heading (H1) per page | No
2. Basic SEO | sitemap.xml and robots.txt are live; search engines are not blocked | No
2. Basic SEO | Site added to Google Search Console and the sitemap submitted | No
2. Basic SEO | A friendly 404 page that links back home | No
3. Speed | Images compressed (WebP/AVIF), none much larger than they appear on screen | No
3. Speed | Videos and 3D load only when scrolled near; nothing heavy before the first screen | No
3. Speed | Only the font weights you use are loaded | No
3. Speed | Google PageSpeed Insights: 80+ on mobile for Home and one case study | No
3. Speed | Tried on a mid-range Android phone on 4G, not only a laptop | No
4. Tracking and data | Analytics installed (e.g. Google Analytics 4 or Plausible) and showing your own visit | No
4. Tracking and data | Key actions tracked: contact form sent, "Book a call" clicks, case study views | No
4. Tracking and data | Contact form delivers to the right inbox (send a real test) | No
4. Tracking and data | Cookie / privacy notice if you use Google Analytics or have EU visitors | No
4. Tracking and data | Privacy policy page linked in the footer | No
4. Tracking and data | Logins (domain, hosting, analytics) have a named owner and are stored safely | No
5. Final testing | Desktop: Chrome, Safari, Firefox and Edge | No
5. Final testing | Phones: iPhone (Safari) and Android (Chrome) | No
5. Final testing | Every link and button clicked once; no dead links | No
5. Final testing | All text proofread; names and numbers checked against the client's figures | No
5. Final testing | Animations smooth, and pages still usable if a 3D scene fails to load | No
5. Final testing | Menus and the form work with the keyboard (Tab key) | No
5. Final testing | The previous version can be restored in one click if launch goes wrong | No